## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | As a system administrator, I want to collect and consolidate hospital data from official government sources so that the dashboard is built on verified and structured data. | MUST HAVE | NA | Tejaswi | Done
S1 | S1 | US-002 | As a data analyst, I want to clean and preprocess raw hospital data so that inconsistencies and missing values do not affect analysis accuracy. | MUST HAVE | US-001 | Nandan | Done
S1 | S1 | US-003 | As a GIS user, I want validated and properly formatted geographic coordinates so that hospitals are plotted accurately on the map. | MUST HAVE | US-002 | Dinesh | Done
S1 | S1 | US-004 | As a project reviewer, I want verified data samples so that I can ensure data reliability before development proceeds. | SHOULD HAVE | US-002 | Shalaka Gangurde | Done
S1 | S1 | US-005 | As a dashboard user, I want hospital attributes classified and grouped logically so that filtering and comparison become easier. | MUST HAVE | US-002 | Gokulnath | Done
S2 | S2 | US-006 | As a project team member, I want clearly defined sprint plans and backlog items so that development tasks are structured and time-bound. | MUST HAVE | NA | Deepak and Pratiksha | Done
S2 | S2 | US-007 | As a project stakeholder, I want user stories to be formally documented so that project requirements are clearly communicated. | MUST HAVE | US-006 | Tulasi Reddy | Done
S2 | S2 | US-008 | As a project team lead, I want the requirement analysis to be documented so that development aligns with project objectives. | MUST HAVE | US-006 | Sai Charan | Done
S3 | S3 | US-009 | As a district health authority user, I want to apply filters (district, beds, facilities) so that I can analyze hospital capacity dynamically. | MUST HAVE | US-002 | Akhila | Done
S3 | S3 | US-010 | As an operations planner, I want a geospatial hospital map so that I can visualize infrastructure distribution across locations. | MUST HAVE | US-003 | Sri Krishna | Done
S3 | S3 | US-011 | As a dashboard user, I want a clean and consistent UI theme so that the system is readable and professional. | MUST HAVE | US-009 | Aditi Yedge | Done
S4 | S4 | US-012 | As a decision-maker, I want KPI cards summarizing key metrics so that I can quickly assess emergency readiness. | MUST HAVE | US-009 | Siva | Done
S4 | S4 | US-013 | As an emergency coordinator, I want a nearest hospital finder module so that patients can be routed efficiently during surge situations. | MUST HAVE | US-010 | Nandan | Done
S5 | S5 | US-014 | As a project evaluator, I want a structured project report so that system functionality and methodology are clearly documented. | MUST HAVE | US-012 | Devi | Done
S5 | S5 | US-015 | As a presentation audience member, I want clear and concise slides so that project insights are easy to understand. | MUST HAVE | US-014 | Tejaswi | Done
S6 | S6 | US-016 | As a quality reviewer, I want unit testing performed on each module so that defects are identified early. | MUST HAVE | US-013 | Pranav | Done
S6 | S6 | US-017 | As a system stakeholder, I want integration testing completed so that all modules function cohesively before final submission. | SHOULD HAVE | US-016 | Dinesh | Done
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 56 | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 5 | 5 | 14 | 8
SPRINT 1 BACKLOG
US-001 | TASK-001 | Identify and verify official government hospital datasets | 2026-02-01 | 2026-02-02 | Tejaswi | Data Gathering | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Consolidate hospital datasets into structured format | 2026-02-02 | 2026-02-03 | Tejaswi | Data Processing | Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-003 | Clean missing and inconsistent values | 2026-02-03 | 2026-02-04 | Nandan | Data Cleaning | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-004 | Validate and correct geographic coordinates | 2026-02-04 | 2026-02-05 | Dinesh | Data Validation | Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-006 | TASK-005 | Define sprint scope and assign backlog items | 2026-02-06 | 2026-02-07 | Deepak and Pratiksha | Planning | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TASK-006 | Document user stories in structured format | 2026-02-07 | 2026-02-08 | Tulasi Reddy | Documentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-007 | Document requirement analysis | 2026-02-08 | 2026-02-09 | Sai Charan | Documentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-009 | TASK-008 | Implement dynamic filter logic for district, beds, and facilities | 2026-02-10 | 2026-02-11 | Akhila | Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0
US-010 | TASK-009 | Develop geospatial hospital map visualization using Plotly | 2026-02-11 | 2026-02-12 | Sri Krishna | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0
US-011 | TASK-010 | Apply UI theme customization and styling enhancement | 2026-02-12 | 2026-02-13 | Aditi Yedge | Development | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
SPRINT 4 BACKLOG
US-012 | TASK-011 | Develop KPI dashboard cards summarizing key hospital metrics | 2026-02-14 | 2026-02-15 | Siva | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
US-013 | TASK-012 | Implement nearest hospital finder logic and routing calculation | 2026-02-15 | 2026-02-16 | Nandan | Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1
SPRINT 5 BACKLOG
US-014 | TASK-013 | Draft structured project report with methodology and findings | 2026-02-17 | 2026-02-18 | Devi | Documentation | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
US-015 | TASK-014 | Design presentation slides summarizing project insights | 2026-02-18 | 2026-02-19 | Tejaswi | Documentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
SPRINT 6 BACKLOG
US-016 | TASK-015 | Conduct unit testing for all application modules | 2026-02-20 | 2026-02-21 | Pranav | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
US-017 | TASK-016 | Perform system integration testing and final validation | 2026-02-22 | 2026-02-23 | Dinesh | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Inconsistencies in raw hospital dataset formatting | Discussed with mentor and agreed on data cleaning approach
S2 | Day 8 | Clarification needed on user story structuring and MOSCOW prioritization | Resolved through discussion and refined backlog entries
S3 | Day 10 | Filter logic not updating map dynamically | Debugged logic and validated filtered dataframe before rendering
S3 | Day 11 | Dark mode UI contrast issue | Adjusted CSS theme variables and tested readability
S5 | Day 13 | Incorrect surge multiplier logic in KPI calculation | Reviewed calculation formula and corrected aggregation logic
S6 | Day 16 | Missing unit test case during validation | Added missing test case and revalidated execution

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-01 | 2026-02-05 | Group - 1 | Introduce structured data validation checklist | Relying on unverified raw datasets | Collaborative dataset review | Implemented validation process before data cleaning
2 | S2 | 2026-02-06 | 2026-02-09 | Group - 1 | Define acceptance criteria clearly during planning | Ambiguity in backlog refinement | Structured sprint planning | Refined user stories with MOSCOW prioritization
3 | S3 | 2026-02-10 | 2026-02-13 | Group - 1 | Perform intermediate testing during feature development | Integrating features without logic validation | Version control discipline | Improved debugging and incremental validation
4 | S4 | 2026-02-14 | 2026-02-16 | Group - 1 | Review calculation formulas before integration | Late-stage logic corrections | Functional module testing | Corrected KPI aggregation logic before deployment
5 | S5 | 2026-02-17 | 2026-02-19 | Group - 1 | Update documentation alongside development | Post-development documentation updates | Structured reporting | Improved documentation alignment with codebase
6 | S6 | 2026-02-20 | 2026-02-23 | Group - 1 | Maintain comprehensive test case tracking | Manual validation without checklist | Final integration testing | Added missing test case and revalidated system