## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Devi | 2026-02-03 | Inconsistent numeric values in hospital bed count column | S1 | Nandan | Logical | Applied numeric conversion with error handling and replaced invalid entries | 2026-02-03 | Closed | Mixed data types identified in raw dataset
2 | Devi | 2026-02-11 | Filter logic not updating map dynamically after selection | S3 | Akhila | Logical | Corrected dataframe filtering logic before rendering map | 2026-02-11 | Closed | Unfiltered dataset passed to visualization
3 | Devi | 2026-02-12 | Dark mode UI contrast affecting readability | S3 | Aditi Yedge | User Interface | Updated CSS theme variables and tested readability | 2026-02-12 | Closed | Color palette misalignment
4 | Devi | 2026-02-15 | Incorrect surge multiplier calculation in KPI metrics | S4 | Siva | Logical | Reviewed aggregation formula and corrected multiplier logic | 2026-02-15 | Closed | Multiplier applied before aggregation
5 | Devi | 2026-02-21 | Missing unit test case for filter module | S6 | Pranav | Others | Added missing test case and revalidated execution | 2026-02-21 | Closed | Identified during final validation

## Sheet2
Logical
User Interface
Maintainability
Standards
Others